## Read Me
Potty Training Guide – Local Authority Project Plan Template
How to use this workbook |  | Progress summary | Value | How calculated
This is a template document - please use as a starting point for your programme planning. Adjust when needed to better suit your programme requirements. |  | Total tasks | 75 | Pre-populated implementation steps
1 | Complete the Setup sheet first. | Complete | 0 | Status = Complete
2 | Use Project Plan as the main working sheet. The steps are pre-populated from the implementation guide. | In progress | 0 | Status = In progress
3 | Assign owners, status, priority and start/end dates. Add or remove tasks to reflect local need. | At risk / blocked | 0 | Needs attention
4 | Enter % complete from 0–100 for each task. | Average % complete | 0 | Mean of task completion values
5 | The Gantt sheet automatically maps tasks across a 52-week view using the dates in Project Plan.
6 | Use milestone flags for major decision points, briefing dates, launch, data collection and reviews.

## Setup
Programme Setup
| Input | Purpose | Example
Local authority / area |  | Area implementing the programme | Example Council
Programme start date |  | Planning anchor for the Gantt view | 01/10/2026
Target public launch date |  | Key public campaign / rollout milestone | 16/04/2027
Target endline data date |  | Target point for outcome data collection | 30/09/2027
Programme manager |  | Day-to-day lead | Name / role
Programme sponsor |  | Senior accountable owner | Name / role
Reporting frequency |  | Formal programme review cadence | Monthly
Primary outcome |  | Headline evaluation measure | Children arriving at Reception fully potty trained [Year 1]
Primary outcome |  | Headline evaluation measure | Children arriving at Reception fully potty trained [Year 2]

## Project Plan
ID | Workstream | Task / step | What this involves | Key output / deliverable | Owner | Status | Priority | Start date | End date | Duration (days) | % complete | Notes / updates/ dependencies
1 | 1. Set-up & governance | Confirm programme case for change | Agree why the programme is needed locally, the intended population and the change sought. | Programme rationale / brief |  | Not started | High |  |  |  | 0
2 | 1. Set-up & governance | Confirm senior sponsorship and governance | Identify sponsor, reporting hierarchy, decision-making route and budget holder. | Governance structure |  | Not started | High |  |  |  | 0
3 | 1. Set-up & governance | Agree reporting and evaluation expectations | Confirm essential outcome measures, reporting audience, cadence and sign-off. | Reporting & evaluation framework |  | Not started | High |  |  |  | 0
4 | 1. Set-up & governance | Complete initial risk assessment | Identify key risks, mitigations and review arrangements. | Signed-off risk assessment |  | Not started | High |  |  |  | 0
5 | 1. Set-up & governance | Complete equality and accessibility review | Review inclusion, language, SEND, accessibility and engagement requirements. | Equality / accessibility actions |  | Not started | High |  |  |  | 0
6 | 1. Set-up & governance | Agree programme non-negotiables | Confirm partnership working, universal messaging, place-based adaptation, face-to-face engagement and evaluation. | Agreed programme principles |  | Not started | High |  |  |  | 0
7 | 2. Core programme team | Appoint core programme team | Assign programme management, data/evaluation, training, communications and operational roles. | Named core team |  | Not started | High |  |  |  | 0
8 | 2. Core programme team | Map partner representation | Identify leaders and contacts across health, education, family services and community partners. | Stakeholder map |  | Not started | High |  |  |  | 0
9 | 2. Core programme team | Agree roles and responsibilities | Clarify responsibilities, decision rights, escalation routes and sector champions. | RACI / responsibility map |  | Not started | High |  |  |  | 0
10 | 2. Core programme team | Assess workforce and admin capacity | Include administration, data follow-up, event support, training and distribution capacity. | Workforce capacity plan |  | Not started | Medium |  |  |  | 0
11 | 2. Core programme team | Set regular programme check-ins | Schedule core-team check-ins and senior / partner update points. | Meeting cadence |  | Not started | Medium |  |  |  | 0
12 | 3. Leadership & sector buy-in | Identify leadership briefing audiences | Segment school/MAT, PVI, childminder, health, GP, pharmacy, family hub and community audiences. | Briefing audience list |  | Not started | High |  |  |  | 0
13 | 3. Leadership & sector buy-in | Prepare leadership briefing content | Cover the case for change, universal messages, local roles, training/support and expectations. | Briefing deck / pack |  | Not started | High |  |  |  | 0
14 | 3. Leadership & sector buy-in | Schedule leadership briefings | Offer suitable dates/times and formats to maximise participation. | Briefing schedule |  | Not started | High |  |  |  | 0
15 | 3. Leadership & sector buy-in | Deliver leadership briefings | Run sessions and capture commitments, questions and actions. | Completed briefings |  | Not started | High |  |  |  | 0
16 | 3. Leadership & sector buy-in | Send briefing follow-up | Provide written information, actions, links and routes for support. | Follow-up communication |  | Not started | Medium |  |  |  | 0
17 | 4. Local context & adaptation | Compile local demographic and service data | Map under-5 population, Reception cohort, funded childcare, SEND/medical needs and local provision. | Local context dataset |  | Not started | High |  |  |  | 0
18 | 4. Local context & adaptation | Identify neighbourhoods / groups with greatest need | Use school, early years, health and deprivation data to understand variation. | Needs map / priority areas |  | Not started | High |  |  |  | 0
19 | 4. Local context & adaptation | Map existing family touchpoints and services | Identify school readiness, health, family hub, nursery, library and community routes. | Service / touchpoint map |  | Not started | Medium |  |  |  | 0
20 | 4. Local context & adaptation | Gather family / practitioner insight | Use existing insight or targeted engagement to understand barriers and preferred support. | Insight summary |  | Not started | Medium |  |  |  | 0
21 | 4. Local context & adaptation | Agree local adaptations | Define local information, translations, accessible formats, targeted outreach and tailored support. | Local adaptation plan |  | Not started | High |  |  |  | 0
22 | 5. Universal messaging & distribution | Confirm universal potty training messages | Agree the core messages and terminology to be used consistently across services. | Approved universal messages |  | Not started | High |  |  |  | 0
23 | 5. Universal messaging & distribution | Identify local information to add | Compile local support routes, contacts and tailored support information. | Local information content |  | Not started | Medium |  |  |  | 0
24 | 5. Universal messaging & distribution | Plan primary offer-day distribution | Decide how guides will reach families receiving school offers. | Offer-day distribution plan |  | Not started | High |  |  |  | 0
25 | 5. Universal messaging & distribution | Estimate print quantities | Use child population and distribution routes to calculate copies with contingency. | Print quantity plan |  | Not started | High |  |  |  | 0
26 | 5. Universal messaging & distribution | Arrange print / direct mail / postage | Obtain quotes, approve artwork and arrange printing, envelopes, postage and logistics. | Print & mailing order |  | Not started | High |  |  |  | 0
27 | 6. Baseline & endline data | Confirm baseline data definitions | Agree definitions for Reception cohort, nappy/pull-up, frequent accidents and diagnosed conditions. | Data definitions |  | Not started | High |  |  |  | 0
28 | 6. Baseline & endline data | Design baseline collection process | Use aggregated/anonymised data and existing reporting routes; confirm GDPR approach. | Baseline data process |  | Not started | High |  |  |  | 0
29 | 6. Baseline & endline data | Collect baseline data | Gather data from schools / agreed sources and follow up gaps. | Baseline dataset |  | Not started | High |  |  |  | 0
30 | 6. Baseline & endline data | Review baseline and target support | Use variation to identify areas or groups where additional support may be needed. | Baseline review |  | Not started | Medium |  |  |  | 0
31 | 6. Baseline & endline data | Schedule endline collection | Set the timetable, responsible owner and communications for endline data. | Endline collection schedule |  | Not started | High |  |  |  | 0
32 | 6. Baseline & endline data | Collect endline data | Repeat the agreed measure after implementation. | Endline dataset |  | Not started | High |  |  |  | 0
33 | 7. Additional data & evaluation | Agree evaluation questions and success measures | Confirm quantitative and qualitative evidence to assess progress and learning. | Evaluation framework |  | Not started | High |  |  |  | 0
34 | 7. Additional data & evaluation | Set up campaign and digital tracking | Create trackable links/QR codes and agree website, social and advertising metrics. | Tracking framework |  | Not started | Medium |  |  |  | 0
35 | 7. Additional data & evaluation | Set up parent feedback routes | Add survey links at parent contact points and plan incentives / focus groups if used. | Parent feedback plan |  | Not started | Medium |  |  |  | 0
36 | 7. Additional data & evaluation | Set up practitioner feedback routes | Build feedback into briefings/training and plan focus groups / sector feedback. | Practitioner feedback plan |  | Not started | Medium |  |  |  | 0
37 | 7. Additional data & evaluation | Set review cadence for evaluation data | Agree when data, gaps, engagement and learning will be reviewed. | Evaluation review schedule |  | Not started | Medium |  |  |  | 0
38 | 8. Marketing materials | Audit available toolkit materials | Review guide, images, GIFs, social assets, ads, flowcharts, posters, postcards and reward chart. | Asset inventory |  | Not started | Medium |  |  |  | 0
39 | 8. Marketing materials | Decide required local edits | Identify logos, service information, translations and accessible formats. | Asset adaptation list |  | Not started | Medium |  |  |  | 0
40 | 8. Marketing materials | Produce / approve localised materials | Complete edits and approvals, including consent processes for any local images/video. | Approved asset pack |  | Not started | High |  |  |  | 0
41 | 8. Marketing materials | Prepare campaign asset schedule | Map which assets will be used by channel and date. | Asset schedule |  | Not started | Medium |  |  |  | 0
42 | 9. Workforce training | Confirm training audiences and model | Decide who needs training, number of sessions, delivery format and train-the-trainer approach. | Training plan |  | Not started | High |  |  |  | 0
43 | 9. Workforce training | Adapt training with local information | Add local services and locally relevant process information. | Localised training pack |  | Not started | Medium |  |  |  | 0
44 | 9. Workforce training | Schedule practitioner training | Choose dates/times to maximise access and include in the programme timetable. | Training schedule |  | Not started | High |  |  |  | 0
45 | 9. Workforce training | Deliver practitioner training | Run sessions and collect learner / facilitator feedback. | Completed training |  | Not started | High |  |  |  | 0
46 | 9. Workforce training | Review training feedback | Identify changes needed for future sessions or wider roll-out. | Training learning log |  | Not started | Medium |  |  |  | 0
47 | 10. Community distribution | Map community distribution partners | Confirm schools, nurseries, childminders, GPs, libraries, family hubs, pharmacies and community locations. | Distribution partner list |  | Not started | High |  |  |  | 0
48 | 10. Community distribution | Set distribution quantities by route | Allocate guides/posters/postcards based on population and expected footfall, with contingency. | Distribution allocation |  | Not started | High |  |  |  | 0
49 | 10. Community distribution | Brief distribution partners | Ensure partners understand programme purpose, messages and signposting. | Partner briefing |  | Not started | Medium |  |  |  | 0
50 | 10. Community distribution | Dispatch materials | Arrange delivery, collection or print-on-demand routes. | Materials distributed |  | Not started | High |  |  |  | 0
51 | 10. Community distribution | Run regular stock checks | Check supply and uptake quarterly, biannually or at a locally appropriate cadence. | Stock monitoring log |  | Not started | Medium |  |  |  | 0
52 | 11. Parent workshops | Confirm workshop model and target audience | Decide locations, frequency, accessibility, child attendance and targeted provision. | Workshop delivery model |  | Not started | High |  |  |  | 0
53 | 11. Parent workshops | Secure venues and facilitators | Use accessible venues and appropriately skilled facilitators. | Venue / facilitator plan |  | Not started | High |  |  |  | 0
54 | 11. Parent workshops | Purchase / assemble workshop resources | Prepare demonstration materials, guides, refreshments and signposting information. | Workshop kit |  | Not started | Medium |  |  |  | 0
55 | 11. Parent workshops | Promote parent workshops | Use trusted local channels, settings, partners and targeted communications. | Workshop promotion plan |  | Not started | Medium |  |  |  | 0
56 | 11. Parent workshops | Deliver parent workshops | Run sessions and collect attendee / facilitator feedback. | Completed workshops |  | Not started | High |  |  |  | 0
57 | 11. Parent workshops | Review attendance and feedback | Assess reach, barriers and changes needed to improve access. | Workshop learning log |  | Not started | Medium |  |  |  | 0
58 | 12. Communications | Create communications plan | Map audiences, messages, channels, timings, responsibilities, budget and measures. | Communications plan |  | Not started | High |  |  |  | 0
59 | 12. Communications | Plan digital and physical channels | Select a balanced mix of partner channels, social/digital, print and other paid media where appropriate. | Channel plan |  | Not started | Medium |  |  |  | 0
60 | 12. Communications | Set paid advertising tests and budget | Define small tests, target audiences and performance measures before scaling spend. | Paid media plan |  | Not started | Medium |  |  |  | 0
61 | 12. Communications | Prepare launch communications | Develop launch content / press release and partner amplification plan. | Launch communications pack |  | Not started | High |  |  |  | 0
62 | 12. Communications | Plan continued parent-facing communications | Schedule repeated messages beyond launch and routes to adapt where engagement is low. | Ongoing communications schedule |  | Not started | Medium |  |  |  | 0
63 | 13. Mobilisation, launch & implementation | Complete mobilisation readiness review | Check team, risks, data, print, training, workshops, distribution, communications and partner readiness. | Readiness checklist |  | Not started | High |  |  |  | 0
64 | 13. Mobilisation, launch & implementation | Publicly launch programme | Activate campaign, partner messaging, distribution and relevant media activity. | Programme launched |  | Not started | High |  |  |  | 0
65 | 13. Mobilisation, launch & implementation | Monitor delivery against plan | Review milestones, risks, budget, workforce capacity and delivery issues regularly. | Progress reports |  | Not started | High |  |  |  | 0
66 | 13. Mobilisation, launch & implementation | Maintain partner communication | Share progress, challenges, successes and actions with sector leaders and partners. | Partner updates |  | Not started | Medium |  |  |  | 0
67 | 13. Mobilisation, launch & implementation | Monitor universal message consistency | Identify message drift and take corrective action where needed. | Message consistency checks |  | Not started | Medium |  |  |  | 0
68 | 13. Mobilisation, launch & implementation | Monitor reach and place-based gaps | Use data and feedback to identify groups/areas missing out and adapt support. | Reach / equity review |  | Not started | High |  |  |  | 0
69 | 13. Mobilisation, launch & implementation | Review and update risk register | Add emerging risks and monitor mitigations throughout implementation. | Updated risk register |  | Not started | High |  |  |  | 0
70 | 13. Mobilisation, launch & implementation | Track budget and resource use | Monitor print, postage, workshops, advertising, incentives and design expenditure. | Budget monitoring |  | Not started | Medium |  |  |  | 0
71 | 14. Evaluation, sustainability & close | Run midpoint programme review | Review progress, data, partner feedback, risks, communications, training, workshops and distribution. | Midpoint review |  | Not started | High |  |  |  | 0
72 | 14. Evaluation, sustainability & close | Analyse endline and evaluation data | Compare baseline/endline outcomes and synthesise supporting quantitative and qualitative evidence. | Evaluation analysis |  | Not started | High |  |  |  | 0
73 | 14. Evaluation, sustainability & close | Share learning with partners | Report what worked, what needs adaptation and implications for future delivery. | Partner learning session / report |  | Not started | Medium |  |  |  | 0
74 | 14. Evaluation, sustainability & close | Agree sustainability plan | Embed ownership, messaging, training, monitoring and support into existing systems. | Sustainability plan |  | Not started | High |  |  |  | 0
75 | 14. Evaluation, sustainability & close | Confirm year-two / business-as-usual actions | Agree recurring annual tasks, budgets, data collection and responsibilities. | BAU action plan |  | Not started | High |  |  |  | 0

## Gantt
Gantt Chart – 52 Week View
 | time axis 0 to 1900-12-22
ID | Workstream | Task | Owner | Status | Start | End | % Complete | time axis 0 to 1900-12-22
1 | 1. Set-up & governance | Confirm programme case for change | 0 | Not started | 0 | 0 | 0 | bar: 0
2 | 1. Set-up & governance | Confirm senior sponsorship and governance | 0 | Not started | 0 | 0 | 0 | bar: 0
3 | 1. Set-up & governance | Agree reporting and evaluation expectations | 0 | Not started | 0 | 0 | 0 | bar: 0
4 | 1. Set-up & governance | Complete initial risk assessment | 0 | Not started | 0 | 0 | 0 | bar: 0
5 | 1. Set-up & governance | Complete equality and accessibility review | 0 | Not started | 0 | 0 | 0 | bar: 0
6 | 1. Set-up & governance | Agree programme non-negotiables | 0 | Not started | 0 | 0 | 0 | bar: 0
7 | 2. Core programme team | Appoint core programme team | 0 | Not started | 0 | 0 | 0 | bar: 0
8 | 2. Core programme team | Map partner representation | 0 | Not started | 0 | 0 | 0 | bar: 0
9 | 2. Core programme team | Agree roles and responsibilities | 0 | Not started | 0 | 0 | 0 | bar: 0
10 | 2. Core programme team | Assess workforce and admin capacity | 0 | Not started | 0 | 0 | 0 | bar: 0
11 | 2. Core programme team | Set regular programme check-ins | 0 | Not started | 0 | 0 | 0 | bar: 0
12 | 3. Leadership & sector buy-in | Identify leadership briefing audiences | 0 | Not started | 0 | 0 | 0 | bar: 0
13 | 3. Leadership & sector buy-in | Prepare leadership briefing content | 0 | Not started | 0 | 0 | 0 | bar: 0
14 | 3. Leadership & sector buy-in | Schedule leadership briefings | 0 | Not started | 0 | 0 | 0 | bar: 0
15 | 3. Leadership & sector buy-in | Deliver leadership briefings | 0 | Not started | 0 | 0 | 0 | bar: 0
16 | 3. Leadership & sector buy-in | Send briefing follow-up | 0 | Not started | 0 | 0 | 0 | bar: 0
17 | 4. Local context & adaptation | Compile local demographic and service data | 0 | Not started | 0 | 0 | 0 | bar: 0
18 | 4. Local context & adaptation | Identify neighbourhoods / groups with greatest need | 0 | Not started | 0 | 0 | 0 | bar: 0
19 | 4. Local context & adaptation | Map existing family touchpoints and services | 0 | Not started | 0 | 0 | 0 | bar: 0
20 | 4. Local context & adaptation | Gather family / practitioner insight | 0 | Not started | 0 | 0 | 0 | bar: 0
21 | 4. Local context & adaptation | Agree local adaptations | 0 | Not started | 0 | 0 | 0 | bar: 0
22 | 5. Universal messaging & distribution | Confirm universal potty training messages | 0 | Not started | 0 | 0 | 0 | bar: 0
23 | 5. Universal messaging & distribution | Identify local information to add | 0 | Not started | 0 | 0 | 0 | bar: 0
24 | 5. Universal messaging & distribution | Plan primary offer-day distribution | 0 | Not started | 0 | 0 | 0 | bar: 0
25 | 5. Universal messaging & distribution | Estimate print quantities | 0 | Not started | 0 | 0 | 0 | bar: 0
26 | 5. Universal messaging & distribution | Arrange print / direct mail / postage | 0 | Not started | 0 | 0 | 0 | bar: 0
27 | 6. Baseline & endline data | Confirm baseline data definitions | 0 | Not started | 0 | 0 | 0 | bar: 0
28 | 6. Baseline & endline data | Design baseline collection process | 0 | Not started | 0 | 0 | 0 | bar: 0
29 | 6. Baseline & endline data | Collect baseline data | 0 | Not started | 0 | 0 | 0 | bar: 0
30 | 6. Baseline & endline data | Review baseline and target support | 0 | Not started | 0 | 0 | 0 | bar: 0
31 | 6. Baseline & endline data | Schedule endline collection | 0 | Not started | 0 | 0 | 0 | bar: 0
32 | 6. Baseline & endline data | Collect endline data | 0 | Not started | 0 | 0 | 0 | bar: 0
33 | 7. Additional data & evaluation | Agree evaluation questions and success measures | 0 | Not started | 0 | 0 | 0 | bar: 0
34 | 7. Additional data & evaluation | Set up campaign and digital tracking | 0 | Not started | 0 | 0 | 0 | bar: 0
35 | 7. Additional data & evaluation | Set up parent feedback routes | 0 | Not started | 0 | 0 | 0 | bar: 0
36 | 7. Additional data & evaluation | Set up practitioner feedback routes | 0 | Not started | 0 | 0 | 0 | bar: 0
37 | 7. Additional data & evaluation | Set review cadence for evaluation data | 0 | Not started | 0 | 0 | 0 | bar: 0
38 | 8. Marketing materials | Audit available toolkit materials | 0 | Not started | 0 | 0 | 0 | bar: 0
39 | 8. Marketing materials | Decide required local edits | 0 | Not started | 0 | 0 | 0 | bar: 0
40 | 8. Marketing materials | Produce / approve localised materials | 0 | Not started | 0 | 0 | 0 | bar: 0
41 | 8. Marketing materials | Prepare campaign asset schedule | 0 | Not started | 0 | 0 | 0 | bar: 0
42 | 9. Workforce training | Confirm training audiences and model | 0 | Not started | 0 | 0 | 0 | bar: 0
43 | 9. Workforce training | Adapt training with local information | 0 | Not started | 0 | 0 | 0 | bar: 0
44 | 9. Workforce training | Schedule practitioner training | 0 | Not started | 0 | 0 | 0 | bar: 0
45 | 9. Workforce training | Deliver practitioner training | 0 | Not started | 0 | 0 | 0 | bar: 0
46 | 9. Workforce training | Review training feedback | 0 | Not started | 0 | 0 | 0 | bar: 0
47 | 10. Community distribution | Map community distribution partners | 0 | Not started | 0 | 0 | 0 | bar: 0
48 | 10. Community distribution | Set distribution quantities by route | 0 | Not started | 0 | 0 | 0 | bar: 0
49 | 10. Community distribution | Brief distribution partners | 0 | Not started | 0 | 0 | 0 | bar: 0
50 | 10. Community distribution | Dispatch materials | 0 | Not started | 0 | 0 | 0 | bar: 0
51 | 10. Community distribution | Run regular stock checks | 0 | Not started | 0 | 0 | 0 | bar: 0
52 | 11. Parent workshops | Confirm workshop model and target audience | 0 | Not started | 0 | 0 | 0 | bar: 0
53 | 11. Parent workshops | Secure venues and facilitators | 0 | Not started | 0 | 0 | 0 | bar: 0
54 | 11. Parent workshops | Purchase / assemble workshop resources | 0 | Not started | 0 | 0 | 0 | bar: 0
55 | 11. Parent workshops | Promote parent workshops | 0 | Not started | 0 | 0 | 0 | bar: 0
56 | 11. Parent workshops | Deliver parent workshops | 0 | Not started | 0 | 0 | 0 | bar: 0
57 | 11. Parent workshops | Review attendance and feedback | 0 | Not started | 0 | 0 | 0 | bar: 0
58 | 12. Communications | Create communications plan | 0 | Not started | 0 | 0 | 0 | bar: 0
59 | 12. Communications | Plan digital and physical channels | 0 | Not started | 0 | 0 | 0 | bar: 0
60 | 12. Communications | Set paid advertising tests and budget | 0 | Not started | 0 | 0 | 0 | bar: 0
61 | 12. Communications | Prepare launch communications | 0 | Not started | 0 | 0 | 0 | bar: 0
62 | 12. Communications | Plan continued parent-facing communications | 0 | Not started | 0 | 0 | 0 | bar: 0
63 | 13. Mobilisation, launch & implementation | Complete mobilisation readiness review | 0 | Not started | 0 | 0 | 0 | bar: 0
64 | 13. Mobilisation, launch & implementation | Publicly launch programme | 0 | Not started | 0 | 0 | 0 | bar: 0
65 | 13. Mobilisation, launch & implementation | Monitor delivery against plan | 0 | Not started | 0 | 0 | 0 | bar: 0
66 | 13. Mobilisation, launch & implementation | Maintain partner communication | 0 | Not started | 0 | 0 | 0 | bar: 0
67 | 13. Mobilisation, launch & implementation | Monitor universal message consistency | 0 | Not started | 0 | 0 | 0 | bar: 0
68 | 13. Mobilisation, launch & implementation | Monitor reach and place-based gaps | 0 | Not started | 0 | 0 | 0 | bar: 0
69 | 13. Mobilisation, launch & implementation | Review and update risk register | 0 | Not started | 0 | 0 | 0 | bar: 0
70 | 13. Mobilisation, launch & implementation | Track budget and resource use | 0 | Not started | 0 | 0 | 0 | bar: 0
71 | 14. Evaluation, sustainability & close | Run midpoint programme review | 0 | Not started | 0 | 0 | 0 | bar: 0
72 | 14. Evaluation, sustainability & close | Analyse endline and evaluation data | 0 | Not started | 0 | 0 | 0 | bar: 0
73 | 14. Evaluation, sustainability & close | Share learning with partners | 0 | Not started | 0 | 0 | 0 | bar: 0
74 | 14. Evaluation, sustainability & close | Agree sustainability plan | 0 | Not started | 0 | 0 | 0 | bar: 0
75 | 14. Evaluation, sustainability & close | Confirm year-two / business-as-usual actions | 0 | Not started | 0 | 0 | 0 | bar: 0

## Lists
Status | Priority | Milestone | Workstream
Not started | High | No | 1. Set-up & governance
In progress | Medium | Yes | 2. Core programme team
At risk | Low |  | 3. Leadership & sector buy-in
Blocked |  |  | 4. Local context & adaptation
Complete |  |  | 5. Universal messaging & distribution
On hold |  |  | 6. Baseline & endline data
7. Additional data & evaluation
8. Marketing materials
9. Workforce training
10. Community distribution
11. Parent workshops
12. Communications
13. Mobilisation, launch & implementation
14. Evaluation, sustainability & close